# 

# Life Cycle Plan (LCP)

**Field Progress Web App**

**Team 04**

|  |  |
| --- | --- |
| **Team Member** | **Role** |
| Uche Uba | Project Manager |
| Mayank Kulkarni | Requirements Engineer |
| Sahithi Velma | System/Software Architect |
| Akanksha Diwedy | Operational Concept Engineer |
| Madhavi Shantharam | Life Cycle Planner |
| Aishwarya Joisa | Feasibility Analyst |
| Kevin Grimes | Website Maintainer, IIV&V, Quality Focal Point |

### Version History

| Date | Author | Version | Changes made | Rationale |
| --- | --- | --- | --- | --- |
| 10/28/2019 | Madhavi Shantharam | 1.0 | Added all the sections required for LCP document | Final draft required for DC Package |

# Table of Contents

[Life Cycle Plan (LCP) i](#_Toc19962805)

[Version History ii](#_Toc19962806)

[Table of Contents iii](#_Toc19962807)

[Table of Tables iv](#_Toc19962808)

[Table of Figures v](#TableOfFigures)

[1. Introduction 1](#_Toc19962810)

[1.1 Purpose of the LCP 1](#_Toc19962811)

[1.2 Status of the LCP 1](#_Toc19962812)

[1.3 Assumptions 1](#_Toc19962813)

[2. Milestones and Products 2](#_Toc19962814)

[2.1 Overall Strategy 2](#_Toc19962815)

[2.2 Project Deliverables 3](#_Toc19962816)

[3. Responsibilities 5](#_Toc19962817)

[3.1 Project-specific stakeholder’s responsibilities 5](#_Toc19962818)

[3.2 Responsibilities by Phase 5](#_Toc19962819)

[3.3 Skills](#_Toc19962820) 9

[4. Approach 11](#_Toc19962821)

[4.1 Monitoring and Control 11](#_Toc19962822)

[4.2 Methods, Tools and Facilities 11](#_Toc19962823)

[5. Resources 13](#_Toc19962824)

[6. Iteration Plan 19](#_Toc19962825)

[6.1 Plan 19](#_Toc19962826)

[6.1.1 Capabilities to be implemented](#_Toc19962827) 20

[6.1.2 Capabilities to be tested](#_Toc19962828) 20

[6.1.3 Capabilities not to be tested](#_Toc19962829) 20

[6.1.4 CCD Preparation Plans](#_Toc19962830) 21

# Table of Tables

[Table 1: Artifacts Deliverables in Exploration Phase 3](#_Toc19962851)

[Table 2: Artifact deliverable in Valuation Phase 3](#_Toc19962852)

[Table 3: Artifact deliverable in Foundations Phase 3](#_Toc19962853)

[Table 4: Artifact deliverable in Development Phase 4](#_Toc19962854)

[Table 5: Stakeholder's Responsibilities in each phase 5](#_Toc19962856)

[Table 6: Module lists and SLOC of each module 13](#modulelists_sloc)

[Table 7: COCOMOII Scale Driver 13](#_Toc19962857)

[Table 8: COCOMOII Cost Driver for Input Module 14](#_Toc19962858)

[Table 9: COCOMOII Cost Driver for Turf Cutting Module 15](#costdriver_turfcutting)

[Table 10: COCOMOII Cost Driver for Output Module 16](#costdriver_output)

[Table 11: COCOMOII Cost Driver for Testing Framework 17](#costdriver_testingframework)

[Table 12: Construction iteration capabilities to be implemented 20](#iterationcapabilities_implemented)

[Table 13: Construction iteration capabilities to be tested 20](#iterationcapabilities_tested)

# Table of Figures

[Figure 1: COCOMO Estimation Result 18](#cocomo_estimation_result)

Introduction

#### Purpose of the LCP

The purpose of the LCP is to help complete the project on time without overrunning costs. At each phase, careful planning is carried out to eliminate any technical debts and reduce risks.  
  
LCP document ensures that the team and clients have the same collective understanding of requirements and timeline to be followed. This helps in achieving the final aim of the project.

#### Status of the LCP

The current version of the LCP is 1.0 which is aimed at finding out the goals of Foundations phase and prepare for Development Phase. This version will be updated with new ICSM phases and as the project progresses.

#### Assumptions

* The duration of the project is 12 weeks in Fall 2019 semester
* We don’t have access to real time voter data. We are developing the algorithm assuming that the test data available with us is very similar to the real time voter information

Milestones and Products

#### Overall Strategy

The Field Progress Web App follows NDI/NCS strategy because we are using these services to develop our core capabilities.

**Exploration phase**

**Duration:** 09/11/2019 – 09/20/2019

**Concept:** Analyzing the proposed system and identification of success critical stakeholders. Identify software requirement, supporting technologies, COTS that could be used and conduct feasibility evidence

**Deliverables**: Website set up, Client interaction meeting notes

**Milestone**: Valuation Commitment Review

**Valuation phase**

**Duration:** 09/20/2019 – 10/04/2019

**Concept:** Define the project scope, develop operational concept, identify win conditions, analyze risk and prepare risk mitigation plan, prototype high risk item

**Deliverables**: Jira Weekly Survey, Project Plan, Progress Report, Risk and Defect Report, Win Conditions, Prototype, Cost Estimation Report

**Milestone**: Foundation Commitment Review

**Foundations phase**

**Duration:** 10/04/2019 – 10/25/2019

**Concept:** Analyze use-cases, produce system and software architecture, project plan, operational concept, feasibility evidence, further prototyping

**Deliverables**: Winbook, Technical Debt Report, Jira Weekly Survey, Project Plan, Progress Report, Risk and Defect Report, Development Commitment Package (OCD, SSAD, FED, LCP), Improved version of the prototype

**Milestone**: Development Commitment Review

**Development phase**

**Duration:** 10/25/2019 – 11/20/2019

**Concept:**  Implement all the required capabilities and test them

**Deliverables**: Core Capability Drive Through report, Transition Readiness report, Jira Weekly Survey, Project Plan, Progress Report, Risk and Defect Report

**Milestone**: Operational Commitment Review

**Operation phase**

**Duration:** 11/20/2019 – 12/06/2019

**Concept:** Prepare for system delivery

**Deliverables:** Final product, necessary documentation

#### Project Deliverables

##### Exploration Phase

Table : Artifacts Deliverables in Exploration Phase

|  |  |  |  |
| --- | --- | --- | --- |
| **Artifact** | **Due date** | **Format** | **Medium** |
| Client Interaction Report | 9/13/2019 | .pdf | Soft copy |
| Team Website | 9/23/2019 | Website | Soft copy |
| Win Conditions | 9/26/2019 | Winbook | Soft copy |

##### Valuation Phase

Table : Artifact deliverable in Valuation Phase

|  |  |  |  |
| --- | --- | --- | --- |
| **Artifact** | **Due date** | **Format** | **Medium** |
| Prototype Presentation Slides | 10/04/2019 | .pptx | Soft copy |
| Cost Estimation LCP | 10/11/2019 | .pdf | Soft copy |
| Cost Estimation V&V | 10/11/2019 | .pdf | Soft copy |
| Project Plan | Bi-weekly 09/25/2019 | .mpp | Soft copy |
| Progress Report | Bi-weekly 09/25/2019 | .xlsx | Soft copy |
| Risk and Defect Report | Bi-weekly 09/25/2019 | .xlsx | Softcopy |
| Jira Weekly Survey | Weekly Monday | Jira ticket | Jira website |

##### Foundations Phase

Table : Artifact deliverable in Foundations Phase

|  |  |  |  |
| --- | --- | --- | --- |
| **Artifact** | **Due date** | **Format** | **Medium** |
| Jira Weekly Summary | Weekly Monday | Jira ticket | Jira Website |
| Project Plan | Bi-weekly 10/09/2019, 10/23/2019 | .mpp | Soft copy |
| Progress Report | Bi-weekly 10/09/2019, 10/23/2019 | .xlsx | Soft copy |
| Risk and Defect Report | Bi-weekly 10/09/2019, 10/23/2019 | .xlsx | Soft copy |
| Team Technical Debt Report | 10/23/2019 | .xlsx | Soft copy |
| Development Commitment Review (DCR) ARB Slides | 10/25/2019 | .ppt | Soft copy |
| Development Commitment Package   * Operational Concept Description (OCD) * Feasibility Evidence Description (FED) * System and Software Architecture Description (SSAD) * Life Cycle Plan (LCP) | 10/28/2019 | .doc, .pdf | Soft copy |
| Winbook and Prioritization report | 10/15/2019 | .xlsx | Soft copy |
| Win Conditions | 10/21/2019 | .pdf | Soft copy |

##### Development Phase

Table : Artifact deliverable in Development Phase

|  |  |  |  |
| --- | --- | --- | --- |
| **Artifact** | **Due date** | **Format** | **Medium** |
| Jira Weekly Summary | Weekly Monday | Jira ticket | Jira Website |
| Project Plan | Bi-weekly 11/06/2019, 11/20/2019 | .mpp | Soft copy |
| Progress Report | Bi-weekly 11/06/2019, 11/20/2019 | .xlsx | Soft copy |
| Risk and Defect Report | Bi-weekly 11/06/2019, 11/20/2019 | .xlsx | Soft copy |
| Core Capability Drive Through Report (CCD) | 11/22/2019 | .pdf | Soft copy |

##### 

Responsibilities

#### Project-specific stakeholder’s responsibilities

Stakeholders for Field Progress Web Application are Client, User, Maintainer, Developers and IIV&V.

#### Responsibilities by Phase

Table : Stakeholder's Responsibilities in each phase

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Team Member / Role** | **Primary / Secondary Responsibility** | | | | |
| **Exploration** | **Valuation** | **Foundations** | **Development-** Construction Iteration | **Development-** Transition Iteration |
| **Name:**  Evan Shulman, Isaac Wang, Nikolaj Baer  **Role:**  Client | **Primary Responsibility**   * Outline the requirements of the desired system * Attend Win-Win Negotiation Session 1 | **Primary Responsibility**   * Attend Win-Win Negotiation Session 2   **Secondary Responsibility**   * Provide voters information based on which algorithm should be implemented | **Primary Responsibility**   * Hold meetings with the development to monitor progress and re-align project goals according to project progress | **Primary Responsibility**   * Provide feedback on DCR prototype and suggest improvements   **Secondary Responsibility**   * Provide necessary platform support for application development | **Primary Responsibility**   * Participate in CCD to have hands experience on the system and provide feedback * Involve other stakeholders (if any, maintainers) and train them |
| **Name:**  Uche Uba  **Role:**  Project Manager | **Primary Responsibility**   * Understand the project scope. Get to know teams’ strengths and weaknesses * Create biweekly project plan, progress report, and risk and defect report * Assign tasks to team members | **Primary Responsibility**   * Create biweekly project plan, progress report, and risk and defect report * Assess high risk features to prototype * Develop Personas for prototype presentation * Prototype implementation – render output of clustering algorithm on MapBox | **Primary Responsibility**   * Create biweekly project plan, progress report, and risk and defect report * Set up React framework and develop front-end of the application * Plan weekly meetings for developing and working on ARB presentation | **Primary Responsibility**   * Help create a development schedule with LCP and ensure that the development progress is on track to be completed before the deadline | **Primary Responsibility**   * Ensure that the transition plan is in place * Prepare the system to be delivered with necessary documentation |
| **Name:**  Mayank Kulkarni  **Role:**  Requirements Engineer | **Primary Responsibility**   * Analyze the system requirements from win- conditions | **Primary Responsibility**   * Prototype - Implement algorithm to form clusters of voters based on number of volunteers * Integrate NDIs and ensure working of prototype * Set up GitHub repository | **Primary Responsibility**   * ARB Prototype - Implement algorithm to form clusters of voters based on number of volunteers within given precincts * Integrate NDIs and ensure working of prototype | **Primary Responsibility**   * Ensure that the ongoing development is in accordance with the requirements * Development of algorithm/user interface | **Primary Responsibility**   * Ensure that the system to be delivered is according to the requirements specified * Prepare comprehensive documentation of the features implemented and not implemented (if any) |
| **Name:**  Sahithi Velma  **Role:**  Software/System Architect | **Primary Responsibility**   * Research different COTS, APIs, and other technologies to be used * Determine whether the different NDIs are interoperable | **Primary Responsibility**   * Prototype implementation – render output of clustering algorithm on MapBox | **Primary Responsibility**   * Develop module architecture for the proposed system * Work on SSAD documentation for DC Package | **Primary Responsibility**   * Ensure that the application being developed is in sync with the architecture and keep it up to date in case of any changes * Development of algorithm/user interface | **Primary Responsibility**   * Review system architecture * Testing of the system |
| **Name:**  Akanksha Diwedy  **Role:**  Operational Concept Engineer | **Primary Responsibility**   * Understand requirements and win conditions * Begin developing the operational concept description | **Primary Responsibility**   * Continue to work on the operational concept description as Win -Win conditions change and evolve | **Primary Responsibility**   * Work on OCD documentation for DC Package * Select optimal NDI for application implementation * ARB Prototype - Integrate the backend framework with the front end * Prepare for prototype presentation | **Primary Responsibility**   * Development of algorithm/user interface * Ensure that the objectives are met as the product is being developed | **Primary Responsibility**   * Check whether all the objectives have been met * Prepare operation phase documentation |
| **Name:**  Madhavi Shantharam  **Role:**  Life Cycle Planner | **Primary Responsibility**   * Determine the responsibilities of each stakeholder * Start building the life cycle plan * Determine the deliverables of each milestone | **Primary Responsibility**   * Discuss with team members to determine the values of factors and calculate the estimated effort using COCOMO II * Prototype - Implement algorithm to form clusters of voters based on number of volunteers * Setup system for prototype presentation | **Primary Responsibility**   * Re-estimate efforts using COCOMO II * Create iteration plan for further iterations in LCP * Work on LCP documentation for DC Package | **Primary Responsibility**   * Create development schedule for product implementation * Implementation of algorithm/user interface | **Primary Responsibility**   * Testing of the product * Prepare transition plan to deliver the product to the clients |
| **Name:**  Aishwarya Joisa  **Role:**  Feasibility Analyst | **Primary Responsibility**   * Determine the feasibility of features proposed by the client and verify whether it is feasible within the given time frame | **Primary Responsibility**   * Analyze NDI and COTS * Determine high risk items and come up with a risk mitigation strategy * Select optimal NDI for implementation of prototype | **Primary Responsibility**   * Work on FED documentation for DC Package * Research API s / NDIs that could be used for product implementation * Develop Personas for prototype presentation | **Primary Responsibility**   * Implementation of algorithm/user interface * Continuously check feasibility of the system | **Primary Responsibility**   * Document NDI/NCS component of the product * Testing of the product |
| **Name:**  Kevin Grimes  **Role:**  Website Maintainer, IIV&V, Quality Focal Point | **Primary Responsibility**   * Build Team Website and keep it up to date * Review win conditions | **Primary Responsibility**   * Ensure that the team website is up to date * Perform Independent Cost Estimation using COCOMO II * Understand the intended behavior of desired capabilities * Verify working prototype | **Primary Responsibility**   * Verify and validate Jira tickets * Verify working prototype * Start preparing test plan to run unit and integration tests on developed modules | **Primary Responsibility**   * Create a test plan * Review code * Perform unit and integration tests | **Primary Responsibility**   * Test the application and ensure that it is ready for delivery * Prepare a quality management document for maintainers to help maintain the application |

#### Skills

|  |  |  |
| --- | --- | --- |
| **Team members** | **Role** | **Skills** |
| Uche Uba | Project Manager | **Current Skills:** Python, JavaScript, Angular, Node  **Required Skills:** Project Management, Python, Django, React, Deck.gl, MS Project, Jira |
| Mayank Kulkarni | Requirements Engineer | **Current Skills:** Python, Django, Winbook  **Required Skills:** Python, Django, React, Deck.gl, Winbook |
| Sahithi Velma | System/Software Architect | **Current Skills:**  Java, Python, Backend Development  **Required Skills:** Python, Django, React, Deck.gl, Analyzing NDI interoperability, UML Modelling, Technical writing |
| Akanksha Diwedy | Operational Concept Engineer | **Current Skills:** Python, Django, Backend Development, ML/AI, Scala  **Required Skills:** Python, Django, React, Deck.gl, Technical writing |
| Madhavi Shantharam | Life Cycle Planner | **Current Skills:**  Python, Java backend development, JavaScript  **Required Skills:** Project/Life Cycle Planning, MS Project, Python, Django, React, Deck.gl, Technical writing, COCOMO II |
| Aishwarya Joisa | Feasibility Analyst | **Current Skills:** Python, Backend Development  **Required Skills:** Python, Django, React, Deck.gl, Technical writing |
| Kevin Grimes | Website Maintainer, IIV&V, Quality Focal Point | **Current Skills:** Python, Jira, Technical Writing, Test Planning  **Required Skills:** Python, Django, React, Deck.gl, Jira, Technical writing, Test Planning |

Approach

#### Monitoring and Control

We use Microsoft Project to prepare the project plan, create tasks in Jira to keep track of all the individual and team activities. We use GitHub repository to review and check-in code. Bi-Weekly Progress reports, and Risk and Defect reports are being prepared to monitor the progress of the project.

##### Closed Loop Feedback Control

Team uses Slack, Gmail to share ideas within the team and to facilitate communication with the clients. All resources and documents are uploaded to a shared Google Drive and to the team website. Also, team members meet at least once in a week to discuss project milestones, progress and provide feedback for each other’s work.

##### Reviews

Team conducts bi-weekly meetings to discuss and review the current project plan and progress, identify any new risks and defects and, assess the goals and issues that needs to be resolved from previous report. We review each other’s work, develop test cases to find bugs and improve code quality. We setup timely meetings with the clients to receive feedback on the ongoing work.

#### Methods, Tools and Facilities

|  |  |  |
| --- | --- | --- |
| **Tools** | **Usage** | **Provider** |
| Project Professional 2016 | Prepare Bi-Weekly Project plan | Microsoft |
| Jira | Create tasks to keep track of planned work and monitor progress and to track defects | USC |
| COCOMO II | Estimate cost and efforts | USC |
| GitHub | Developers to collaborate on Software Development | GitHub |
| Microsoft Excel | To create Progress report, and Risk and Defect Report | Microsoft |
| Slack | Team and Client communication | Slack |
| Zoom Meetings | Video conferencing with DEN Students and Clients | Zoom |
| Winbook | Add/Prioritize Win Conditions | USC |
| Visual Paradigm | Create UML Models | USC |
| Balsamiq | Create UI Mockups | Balsamiq |
| React | JavaScript library for creating UI Interfaces | React |
| Django | Backend server | Django |
| Deck.gl/MapBox | MapBox is used to render clusters of voters on a map based view.Deck.gl is used to provide visualizations on top of MapBox based maps. | Open Source |

#### 

### Resources

* Estimated CSCI577a Effort: 7 team members at 12 hours/week for 12 weeks.

Increased efforts per/team member, per/week with the increase in scope of the project

(need for an input module) from previous cost estimation specification.

* Total estimated effort: 1008 hours
* Budget information: We currently don’t have any defined budget i.e. budget is $0
* Project duration: 12 weeks
* Component modules: Input Module, Turf Cutting Module, Output Module and Testing Framework
* Programming language used: Python, JavaScript

Table 6: Module lists and SLOC of each module

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **Module Name** | **Brief Description** | **SLOC** |
| 1 | Input module | Provide an interface for the users to input volunteer information | 500 |
| 2 | Turf cutting module | Clustering of voter data within the given precincts | 400 |
| 3 | Output module (Visualization) | Provide an interface for the users to view the cut turfs visually in a map-based view | 400 |
| 4 | Testing framework (internal use) | Build a testing framework for validating the system for its effectiveness both module wise and integration with each other | 200 |

Table 7: COCOMOII Scale Driver

|  |  |  |
| --- | --- | --- |
| **Scale Driver** | **Value** | **Rationale** |
| PREC | NOMINAL | Team is familiar with some technologies like usage of Google Maps API. However, there is a need for innovative data processing architectures, and algorithms to accommodate the requirements of this project |
| FLEX | NOMINAL | The Development team is given a lot of leeway in how they want to implement the project, but the final product must plug into Field Progress’ existing tech stack. So, there is a need for Software conformance with external interface specifications |
| RESL | HIGH | All critical risk items, schedule and internal milestones are identified. However, there is a potential risk in implementing certain features cutting turfs based on walkability, availability of the volunteers, the type of terrain among others. We plan to have regular sync ups with clients and collaborative brainstorming to resolve this risk |
| TEAM | HIGH | We have the Win-Win negotiations in place to minimize the conflicts. Also, each stakeholder has considerable consistency of objectives and willingness to accommodate each other’s objectives |
| PMAT | NOMINAL | We are at Maturity Level 1 |

Table 8: COCOMOII Cost Driver for Input Module

|  |  |  |
| --- | --- | --- |
| **Cost Driver** | **Value** | **Rationale** |
| RELY | HIGH | Turf cutting and Visualization modules depend on this module. The effect of software failure is high, as without input other modules cannot function |
| DATA | NOMINAL | Input to the system from user interface includes volunteer information like name, availability, walkability, and others Approx. 500 SLOC to provide an interface to take in this input data. Keeping an average window of 5 to 50 volunteers per transaction, test data will not exceed approx. 1200 Bytes. D/P = 2.4 |
| DOCU | NOMINAL | Development process follows ICSM, the document for life-cycle needs is normal. |
| CPLX | NOMINAL | Simple UI component which takes in user input |
| RUSE | NOMINAL | Interface to take the input is specific to the application being designed. |
| TIME | NOMINAL | System should be able to take in user data in a considerable time. <50% of the available execution time |
| STOR | NOMINAL | Should have the capability to store the provided input as it in turn serves as an input to the algorithm. <50% of available storage |
| PVOL | LOW | Creates a dynamic array for the Volunteer info in React |
| ACAP | NOMINAL | Development team was quite good in gathering the requirements and producing a high-level design of the product to be developed |
| PCAP | NOMINAL | Development team was able to choose the COTS to be used in the project implementation in a collaborative way |
| PCON | NOMINAL | Not quite risky as it is a 12-week project and team members are committed to course guidelines |
| APEX | LOW | Development team has very little experience in building this kind of application |
| LTEX | NOMINAL | Few team members have prior experience in building Python applications. But we are learning React.js to implement front-end of the application and integrate it with the back-end |
| PLEX | NOMINAL | Few team members have experience working on Django. However, we are not familiar with React and integrating Django and React |
| TOOL | NOMINAL | Team is familiar in using some software tools like GitHub, Slack. However, tools like Microsoft Project, Jira is new for most of the team members |
| SITE | HIGH | Team consists of 6 on-campus and 1 off-campus student. Team collaboration has never been a problem as the team is proficient in using tools for video conferencing and exchanging emails for communication |
| SCED | NOMINAL | The schedule is set at 12 weeks and we are not planning on stretching out |

Table 9: COCOMOII Cost Driver for Turf Cutting Module

|  |  |  |
| --- | --- | --- |
| **Cost Driver** | **Value** | **Rationale** |
| RELY | NOMINAL | If the turf cutting fails, campaign managers will have to resort to cutting the turfs manually. This could cost Field Progress quite a bit of money and reputation, as this functionality is a major piece of their offering. So, providing a reliable algorithm is quite important |
| DATA | VERY HIGH | Input to the system includes thousands of entries of voter data consisting of latitudes, longitudes and precincts and volunteer information like no. of volunteers, availability, capability etc.  Approx. 400 SLOC to process the input and cut turfs. D/P > 1000 |
| DOCU | NOMINAL | Because the development process follows ICSM, the document for life-cycle needs is normal. |
| CPLX | HIGH | This involves implementation of clustering algorithms with input parameters such as volunteer availability, terrain, walkability, and calls to APIs to obtain the distance and other information. |
| RUSE | NOMINAL | Algorithm should be designed in such a way that it could be plugged into Field Progress’ existing stack |
| TIME | VERY HIGH | We will be running complex algorithms on considerably huge amount of data. Application is expected to use almost 85% of the available execution time |
| STOR | NOMINAL | Less than 50% of the available storage will be used |
| PVOL | LOW | As we are using Python libraries for implementation of algorithm, it may not be too dependent on the underlying platform |
| ACAP | NOMINAL | Development team was quite good in gathering the requirements and producing a high-level design of the product to be developed |
| PCAP | NOMINAL | Development team was able to choose the COTS to be used in the project implementation in a collaborative way |
| PCON | NOMINAL | Not quite risky as it is a 12-week project and team members are committed to course guidelines |
| APEX | LOW | Development team has very little experience in building this kind of application |
| LTEX | NOMINAL | Few team members have prior experience in building Python applications. But we are learning React.js to implement front-end of the application and integrate it with the back-end |
| PLEX | NOMINAL | Few team members have experience working on Django. However, we are not familiar with React and integrating Django and React |
| TOOL | NOMINAL | Team is familiar in using some software tools like GitHub, Slack. However, tools like Microsoft Project, Jira is new for most of the team members |
| SITE | HIGH | Team consists of 6 on-campus and 1 off-campus student. Team collaboration has never been a problem as the team is proficient in using tools for video conferencing and exchanging emails for communication |
| SCED | NOMINAL | The schedule is set at 12 weeks and we are not planning on stretching out |


Table 10: COCOMOII Cost Driver for Output Module

|  |  |  |
| --- | --- | --- |
| **Cost Driver** | **Value** | **Rationale** |
| RELY | NOMINAL | Visualization is important as it provides the user to view the output of the algorithm i.e. turf cutting in a map view. Plan is to plug in the data into visualization tools like mapbox/deck.gl |
| DATA | HIGH | Test data would be GeoJSON list of voters returned by the turf cutting algorithm. Approx. 400 SLOC to process the response and render it on the map. Approx. D/P between 100 and 1000 |
| DOCU | NOMINAL | Because the development process follows ICSM, the document for life-cycle needs is normal. |
| CPLX | HIGH | Involves integration of output from Django server with UI designed using React |
| RUSE | LOW | Required for verification during development cycle. May or may not be required after integrating with actual output module on Field Progress’ tech stack |
| TIME | NOMINAL | Less than 50% of the available execution time |
| STOR | NOMINAL | Less than 50% of the available storage will be used |
| PVOL | NOMINAL | Browser and COTS upgrades might pose a potential risk. However, they are not prone to change very frequently |
| ACAP | NOMINAL | Development team was quite good in gathering the requirements and producing a high-level design of the product to be developed |
| PCAP | NOMINAL | Development team was able to choose the COTS to be used in the project implementation in a collaborative way |
| PCON | NOMINAL | Not quite risky as it is a 12-week project and team members are committed to course guidelines |
| APEX | LOW | Development team has very little experience in building this kind of application |
| LTEX | NOMINAL | Few team members have prior experience in building Python applications. But we are learning React.js to implement front-end of the application and integrate it with the back-end |
| PLEX | NOMINAL | Few team members have experience working on Django. However, we are not familiar with React and integrating Django and React |
| TOOL | NOMINAL | Team is familiar in using some software tools like GitHub, Slack. However, tools like Microsoft Project, Jira is new for most of the team members |
| SITE | HIGH | Team consists of 6 on-campus and 1 off-campus student. Team collaboration has never been a problem as the team is proficient in using tools for video conferencing and exchanging emails for communication |
| SCED | NOMINAL | The schedule is set at 12 weeks and we are not planning on stretching out |

**Table 11: COCOMOII Cost Driver for Testing Framework**

|  |  |  |
| --- | --- | --- |
| **Cost Driver** | **Value** | **Rationale** |
| RELY | NOMINAL | Testing is a fairly important component as it defines the quality of the product. Testing framework must be good enough to catch any bugs and ensure that the product is working as expected |
| DATA | HIGH | Requires good amount of test data to test all modules of the product individually and integration between them. Approx. 200 SLOC of unit and integration test functions. Approx. D/P between 100 and 1000 |
| DOCU | NOMINAL | Because the development process follows ICSM, the document for life-cycle needs is normal. |
| CPLX | NOMINAL | Unit tests to verify working of each module separately and integration with one another to test the end to end functionality |
| RUSE | NOMINAL | Could be reused/extended by maintainer if there comes a need to verify any issues or test any additional functionality |
| TIME | NOMINAL | Less than 50% of the available execution time |
| STOR | NOMINAL | Less than 50% of the available storage will be used |
| PVOL | NOMINAL | Test scripts are not too dependent on the underlying platform. However, it might need changes if the core functionality changes which is not highly prone to changes |
| ACAP | NOMINAL | Development team was quite good in gathering the requirements and producing a high-level design of the product to be developed |
| PCAP | NOMINAL | Development team was able to choose the COTS to be used in the project implementation in a collaborative way |
| PCON | NOMINAL | Not quite risky as it is a 12-week project and team members are committed to course guidelines |
| APEX | LOW | Development team has very little experience in building this kind of application |
| LTEX | NOMINAL | Few team members have prior experience in building Python applications. But we are learning React.js to implement front-end of the application and integrate it with the back-end |
| PLEX | NOMINAL | Few team members have experience working on Django. However, we are not familiar with React and integrating Django and React |
| TOOL | NOMINAL | Team is familiar in using some software tools like GitHub, Slack. However, tools like Microsoft Project, Jira is new for most of the team members |
| SITE | HIGH | Team consists of 6 on-campus and 1 off-campus student. Team collaboration has never been a problem as the team is proficient in using tools for video conferencing and exchanging emails for communication |
| SCED | NOMINAL | The schedule is set at 12 weeks and we are not planning on stretching out |

Figure 1: COCOMO Estimation Result



**Estimated Size**: 1500 SLOC

**Estimated Effort**:   
Optimistic: 4.7 person-month x 152 = 714.4 person-hr

Most Likely: 5.8 person-month x 152 = 881.6 person-hr

Pessimistic: 7.3 person-month x 152 = 1109.6 person-hr

**Estimated Schedule**:

Total work time of the whole team = 12 hr/week x 4 weeks x 7 team members = 336 hr/month

Optimistic: 714.4 / 336 = 2.12 month

Most Likely: 881.6 / 336 = 2.6 month

Pessimistic: 1109.6 / 336 = 3.3 month

Thus, most likely we need 2.6 month to complete this project which is no longer than the length of one semester. However, the actual work time may be longer than that. If each team member can stretch a little more than 12 hr/week, we can avoid falling into Pessimistic estimates (which is little longer than one semester) thereby not scoping down or stretching out on the project schedule.

**Note**: - This is a revised estimate after considering increase in scope and complexity from the previous version of cost estimation

# 6. Iteration Plan

## 6.1 Plan

As we move ahead to the Development Phase, we are planning on enhancing the current Prototype for Turf Cutting.

Development Phase will consist of two iterations. First being, implementation of all the remaining core capabilities. This includes design and implementation of an efficient algorithm to take volunteer info, voter info, and other parameters like likelihood of conversation, terrain among others as input and produce a sub list of volunteers mapped to voters. This output must be rendered on a map view which shows turfs cut within each precinct as area-covered by polygons (Visualization purposes only, not delivered as part of the project). This iteration also includes testing of the modules individually i.e. unit tests and all the modules integrated i.e. integration tests

Second iteration aims at preparing the application to be handed over to the client. This involves exhaustive testing of the algorithm to ensure that all the desired functionalities are working as expected when the algorithm is plugged into Field Progress’ tech stack.

### 6.1.1 Capabilities to be implemented

Table 12: Construction iteration capabilities to be implemented

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **ID** | **Capability** | **Description** | **Priority** | **Iteration** |
| 1 | Implementation of algorithm | User should be able to generate turfs | Very High | 1 |
| 2 | Input interface | User should be able to provide volunteer information into the system | High | 1 |
| 3 | Output interface | User should be able to view the cut turfs on a map-based view | High | 1 |

### 6.1.2 Capabilities to be tested

Table 13: Construction iteration capabilities to be tested

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **ID** | **Capability** | **Description** | **Priority** | **Iteration** |
| 1 | Input Interface | Verify whether user can provide inputs using the input interface | Very High | 1 |
| 2 | Turf Cutting | Verify whether turfs are cut efficiently | Very High | 1 |
| 3 | Output Interface | Verify whether user can view the cut turfs on a map-based view with zoom in and zoom out options | High | 1 |
| 4 | End-End flow | Verify whether end-end flow of the app is working as desired | Very High | 1 |
| 5 | Performance | Verify efficiency of the algorithm in terms of execution time | High | 2 |
| 6 | Compatibility | Verify whether algorithm output when plugged into Field Progress’s stack produces the desired result | Very High | 2 |
| 7 | API Testing | Since the main deliverable is the algorithm in the form of a library, verify whether the user can access this library to access/fetch the desired information | Very High | 1 |

### 6.1.3 Capabilities not to be tested

All the capabilities mentioned above will be tested to ensure that performance of the algorithm is efficient both in terms of accuracy and execution time.

### 6.1.4 CCD Preparation Plans

* Implement and test all the features as per client’s requirement specification. Ensure that the system is well tested and there are no bugs
* Prepare a demonstrational workflow for the client to use the system. This involves ensuring that integration of all the modules are in place
* During CCD, clients get a chance to use the application. They can input volunteer information into the said system via an input interface designed using React, generate turfs and view the cut turfs on a map generated using Deck.gl.
* Receive feedback from the clients and course faculty. Incorporate any necessary changes in accordance with client’s feedback
* Prepare for the final delivery of the system