## SLOC
Team Number: | 4
Week: | 2
Program Size (SLOC) | Actual
Base | 0
Added | 18
Deleted | 0
Modified | 0
Reused | 0
From COTS | 12
Total New SLOC | 30

## COTS
List of third-party components being considered for use in the system as of 09/25/2019
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
Panda | For data processing | Pip | Database and Mapbox | TRUE
Django | Creating a server to host the application | Pip | Database, AWS |  |  | TRUE
AWS | To host the server |  | MapBox, Python libraries, PostGIS | TRUE
React | For the User Interface and data rendering | npm | MapBox, Deck.gl, Python
Javascript Libraries | For the User Interface and data rendering along with HTML and CSS |  | AWS & MapBox |  |  | TRUE
Kepler.gl | Map Visualization |  | AWS & MapBox | TRUE
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
Deck.gl | MapBox and deck.gl proved to integrate better with jupyter notebook |  | deck.gl has a python wrapper built around it to integrate python using jupyter notebook
MapBox | More customizable than google maps. Would be great for visualization |  | MapBox has open soucre features
N/A | N/A |  | N/A
N/A | N/A |  | N/A
N/A | N/A |  | N/A

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Meet with the clients to discuss project progress and direction
2 | Reevaluate current Architecture
3 | Come to a consensus on how the UI should be rendered
4 | Do further work on the Clustering algorithm to indicate Precincts
5 | Start Working on documents required for the ARB
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | How the team will proceed with the project after meeiting with the clients
2 | How the UI will be implemented, and what tool/stack will be used
3
4
5
C. | List your accomplishments from the previous week
1 | Completed a prototype presentation that helped the team gain more clarity on the project
2 | Completed Use case analysis for the project, which helped the team understand how the pruduct will prontentially be used
3 | Implemented a clustering algorithm with results that shall be used as basis for further iterations down the line
4 | Integrated mapbox with jupyter notebook in order to see result of the algorithm
5
6
7
8