## Risk
Top Project Risks as of 10/09/2019
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 | - | Lack of developer experience in building UI | The number of developers on the team that know how to build a rich UI might be limited | Figure out what framework would be used for the front end and assign a subset of the team to learning the framework | 8 | 7 | 56 |  | 1
3 | 2 | Limited set of voter data for testing | Currently, the amount of voter data available for testing in various geographical locations is limited (1 file), so testing the algorithm with different geographical locations would not be as robust | Request more data from the client, so the development team isn't just limited to a list of voters in San Diego | 3 | 6 | 18 | Confidence in the clients to provide us with more voter data when requested | 2
2 | 1 | Method of clustering geographical entity | Clustering turfs based on various constraints could pose a problem during Algorithm development | Determining heuristics vs features to extract from AI model. Compare for better accuracy | 7 | 8 | 56 |  | 2
6 | 4 | Algorithm scalability | Lack of appropriate real world data with considerable size | Testing the performance of the algorithm with a robust set of data | 3 | 6 | 18 | Clients informed the team that an upper bound would be placed on the number of voters to be considered | 2
4 | - | Architecture change | As a result of the client giving the green light to develop a UI that would be web based, the current established architecture could change, potentially causing problems down the line | A developer meeting to figure out a feasible architecture that would work with the new functionalities included | 4 | 5 | 20 |  | 1
5 | - | Integration of All COTS tools | As the project eveolves and develops, some additional COTS tools would potentially be implemented, causing integration issues down the line | Continually sompare and test COTS libraries, and ascertain which ones would work efficiently relative to the project scope | 6 | 9 | 54 |  | 1
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3
4
5