## SLOC
Team Number: | 4
Week: | 5
Program Size (SLOC) | Actual
Base | 0
Added | 200
Deleted | 0
Modified | 50
Reused | 100
From COTS | 40
Total New SLOC | 390

## COTS
List of third-party components being considered for use in the system as of 11/06/2019
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
Panda | For data processing | Pip | Database and Mapbox | TRUE
Django | Creating a server to host the application | Pip | Database |  |  | TRUE
React | For the User Interface and data rendering | npm | MapBox, Deck.gl, Python
MapBox | Map Visualization | npm | React | TRUE
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
MapBox | More customizable than google maps. Would be great for visualization |  | MapBox has open source features
React | Using React to render the map on UI |  | Open Source
Django | Web Framework |  | Open Source
N/A | N/A |  | N/A

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Dry Run for the CCD among team
2 | Evaluating algorithms and COTS to implement availability feature
3 | Increase effeciency of the clustering algorithm
4 | Continue working on documents required for the Final Presentation
5 | Improvising the UI component
6 | Making frontend and backend integration more robust.
B. | List dependencies or things/decision that you waiting for in this week
1 | Efficicent implementation of availability
2 | Discussion on implementation of hierarchical clustering
3
4
5
C. | List your accomplishments from the previous week
1 | Coding K-means clustering algorithm
2 | Partial front end coding in React
3 | Clarifications on features through a meeting with clients
4
5
6