## Risk
Top Project Risks as of 09/25/2019
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 | 1 | Method of clustering geographical entity | conflicts between making the algorithm based on AI method or using any heuristic for turf cutting | Determining heuristics vs features to extract from AI model. Compare for better accuracy | 7 | 8 | 56 |  | 1
2 | 2 | The dataset being provided to base the algorithm on is not real voter data but manual generated data | Confidential voter data | Negotiate for actual voter data. Putting validation checks for actual data match with manual data on which algorithm will be based on. | 4 | 6 | 24 |  | 1
3 | 3 | Visualization | lacks clarity on what all should be shown | Discuss with clients | 3 | 5 | 15 |  | 1
4 | 4 | Algorithm scalability | Lack of appropriate real world data with considerable size | Testing the performance of the algorithm with a robust set of data | 5 | 6 | 30 |  | 1
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3
4
5