## SLOC
Team Number: | 4
Week: | 5
Program Size (SLOC) | Actual
Base | 0
Added | 150
Deleted | 0
Modified | 0
Reused | 80
From COTS | 25
Total New SLOC | 255

## COTS
List of third-party components being considered for use in the system as of 10/23/2019
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
Panda | For data processing | Pip | Database and Mapbox | TRUE
Django | Creating a server to host the application | Pip | Database |  |  | TRUE
React | For the User Interface and data rendering | npm | MapBox, Deck.gl, Python
MapBox | Map Visualization | npm | React | TRUE
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
MapBox | More customizable than google maps. Would be great for visualization |  | MapBox has open source features
React | Using React to render the map on UI |  | Open Source
Django | Web Framework |  | Open Source
N/A | N/A |  | N/A

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Dry run of the ARB presentation with the Clients
2 | Re-evaluate current Architecture
3 | Evaluating algorithms and COTS to implement walkability feature
4 | Do further work on the Clustering algorithm to indicate Precincts
5 | Continue working on documents required for the ARB
6 | Building UI component
7 | Integrating frond-end with the back-end to render results on the map
8
B. | List dependencies or things/decision that you waiting for in this week
1 | How we are going to implement walkability considering the given parameters
2 | Discussion on limitation of mapbox and plan to use alternatives like Google map api
3
4
5
C. | List your accomplishments from the previous week
1 | Prioritization of Win-Win Negotiations
2 | Listed out the Technical Debts at this point in the project cycle
3 | Set up Django Server
4 | Set up React
5 | Prepared for ARB presentation
6
7
8