## Risk
Top Project Risks as of 10/23/2019
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 | 1 | Method of clustering geographical entity | Clustering turfs based on various constraints could pose a problem during Algorithm development | Determining heuristics vs features to extract from AI model. Compare for better accuracy | 7 | 8 | 56 | N/A | 4
3 | 2 | Lack of developer experience in using React and Django | Team members have no prior experience in building applications using React and Django | Team members are learning to work with React and Django | 5 | 7 | 35 | Team members are learning to work with React and Django | 3
2 | 4 | Risk of Incompatibility between React and Django | The back end has to be connected to the front end for rendering output of the algorithm on the UI | Think about alternative COTS incase React and Django integration doesn't happen as expected | 5 | 8 | 40 | Decided on which COTS products we are going to be using | 3
3 | 2 | Architecture change | As a result of the client giving the green light to develop a UI that would be web based, brainstorming on the technologies to be used and user interface design there had to be a restructuring of the architecture | Team members met frequently to restructure the architecture by discussing the possibilities | 3 | 6 | 18 | We restructured major part of the architecture and included the UI | 3

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3
4
5