## Technical Debt
Technical Debt
Describe technical debt of your project :
| 1. Please describe your technical debt in Description | 4. Answer Yes/No on Has it been fixed?
| 2. Catgorize the technical debt based on Category 1 dropdown listbox | 5. If yes, how long did you spend(in hours), if not how long you are you estimating it will take to fix(in hours)?
| 3. Catgorize the technical debt based on Category 2 dropdown listbox | 6. Explain how did you fix it, or your mitgation plan if not fixed.
7. Report No of weeks active.
If you report the debt previously, please update its current status.
List your technical debt
# | Description | Category1 | Category2 | Has it been fixed? | How did you fix it/mitgation plan | No. of weeks active | Reckless _Deliberate | Life Cycle Management Shortfalls | Yes
1 | Lack of real time test data | Methods, Processes and Tools (MPT) Shortfalls | Prudent_Deliberate | No | Trying to obtain real time data from clients | 6 | Reckless_Inadvertent | Personnel Shortfalls | No
2 | Visualisation done on Jupyter notebook for viewing results of the algorithm, but it needs to be integrated with react | Methods, Processes and Tools (MPT) Shortfalls | Prudent_Deliberate | No | We are working on integrating MapBox with React | 4 | Prudent_Inadvertent
4 | There are no unit/integration test modules | Life Cycle Management Shortfalls | Reckless_Inadvertent | No | Learning to build the test modules and write YAML files | 4
5 | Bash script to run the algorithm and provide number of volunteers and precinct as the input | Life Cycle Management Shortfalls | Prudent_Inadvertent | No | Learning to write the bash script to do the same | 2
8
9
10

## Category1_Examples
Description | Examples
Life Cycle Management Shortfalls: | •Debt resulted from schedule pressure due to scope creep where additional features are added without altering the project scope and schedule.
This includes any debt resulted from the software life cycle management shortfalls such: budgeting, requirements, contracts, scheduling, etc. | •Debt resulted from a third-party-estimate where a technical lead make an ignorant- estimation on how long it will take and cost to developed and the actual team are held responsible for these estimation.
•This might include not preforming an automated testing due to schedule pressure, having duplicated code since there is no time to refactor,etc.
Personal Shortfalls:
This includes any debt resulted from people shortfalls | •Debt resulted from the project team such as adding or removing a team member.
such as: not having enough experience, change in team composition,etc. | •Debt resulted from the project team skills such as not having enough experience with the development language.
•This might include: Delaying unit testing until the new tester join the team, not preforming unit testing due to lack of experience.
Methods, tools, and process Shortfalls:
This include any debt resulted from Methods, tools, and process Shortfalls: such as tools limitations, process nature, etc. | •Debt resulted from tool limitation such as the inability to integrate with the API.
• Debt resulted from the process such as : not testing the code until the last minute since we are using waterfall
•This might include: delaying testing due to the process, delaying integration, not following the architecture specification due to language limitations

## Technical Debt Example
Technical Debt
Describe technical debt of your project :
| 1.Please describe your technical debt in Description | 4.Answer Yes/No on Has it been fixed?
| 2. Catgorize the technical debt based on Category 1 dropdown listbox | 5.If yes, how long did you spend(in hours), if not how long you are you estimating it will take to fix(in hours)?
| 3. Catgorize the technical debt based on Category 2 dropdown listbox | 6. Explain how did you fix it, or your mitgation plan if not fixed.
7.Report No of weeks active.
If you report the debt previously, please update its current status.
List your technical debt
# | Description | Category1 | Category2 | Has it been fixed? | How did you fix it/mitigation plan | No. of weeks active | Reckless _Deliberate | Life Cycle Management Shortfalls | Yes
1 |  | Life Cycle Management Shortfalls | Prudent_Deliberate | No | We are working on the English version, and will provide the client with a detailed technical explanation on how to support other languages | 10 | Reckless_Inadvertent | Personnel Shortfalls | No
2 | [6 empty] | Prudent_Deliberate | Methods, Processes and Tools (MPT) Shortfalls
3 | [6 empty] | Prudent_Inadvertent
4
5
6
7
8
9
10