## Sheet1
Team 4
Objectives Span | 09/25 - 10/08
| Objectives | Description | Person/People Assigned | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08
| Win-Win | Have the second win-win negotiation witht the client on 09/26/2019 | Clients and Team | bar: 2019-09-25 to 2019-09-26
| Architecture | Design the system architecture for the project, and specify what components will be used throught the architecture | Team- Led by the System Architect | bar: 2019-09-26 to 2019-09-28
| Sub-Teams | Break the team members into sub teams that will work on various components of the project architecture | Team- Led by the Program Manager | bar: 2019-09-28 to 2019-09-30
| Prototype | Build a prototype for the project to be submitted in class on 10/24/2019 | Team | bar: 2019-09-30 to 2019-10-04
| Algortithm | Decide on whether to go with a heuristic algorithm, or use an ML algorithm for voter clustering | Team. Endorsed by the Feasibility Analyst | bar: 2019-10-03 to 2019-10-08